## Support Case 2012
| Last updated: | 2012-10-24
No. | Issue | EQX Process | Register Date | Target Date | Occurs | Category | Requester/Initiator | Group | Priority | Status | Escalated | Fixed in version | Detail
1 | ES06 Share Mem | ES06 | 2012-10-10 | 2012-10-10 | 1 | Config | Atchara Kanlueang | Niobe | normal | closed | Coke | none | - Forgot delete .bak file config (fixed by user)
2 | O&M Share Knowleadge | E03,E04,E06 | 2012-10-10 | 15/10/2012 19/10/2012 | 2 | Training | Ratthakarn Prathumjorn Phatcharee Sittisanwattanachai | Biz Live Phoebe | normal | closed | Coke Pepsi | none | - Share knowledge
3 | ES05 Length Limit | ES05 | 2012-10-10 | 2012-10-19 | 2 | BUG | Ratthakarn Prathumjorn | Biz Live | normal | on progress | Mig |  | - If message length from AF is larger than …, ES05 does nothing. - This problem is on ES00 (and ES04) since it can't received "chunked" data response from HTTP server (EC02)
4 | URL Configuration | ES04,ES05 | 2012-10-10 | 2012-10-19 | 1 | UR | Ratthakarn Prathumjorn | Biz Live | normal | opened | Tome |  | - Waiting for analysis
5 | ES07 AVP Command | ES07 | 2012-10-10 | 2012-10-19 | 1 | Knowledge | Ekachai Lanamkum | Phoebe | normal | gathering | Tome |  | - Need to discuss with user - Forget to ask this question from user - I think user completely forget about this case either
6 | XML Tag Error | E01 | 2012-10-10 | 2012-10-11 | 1 | AF | Ekachai Lanamkum | Phoebe | normal | closed | Coke | none | - Data is not well form xml standard
7 | E01 Error (key) | E01 | 2012-10-10 | 2012-10-11 | 3 | BUG | Pinit Wongmaneerat Surasuk Kerdphon Natthaporn Pakdee Pattanun Nisakul | Niobe QA QA QA | high | closed | Tome | E01 v1.0.1 | - Returned key0 is incorrect - This problem is found when sizeof key0-4 is larger than 20 - E01 now trim data in key0-4 to 20 if it is larger than 20
8 | Equinox Internal support | ES04,ES05 | 2012-10-10 | 2012-10-15 | 1 | Training | Thawatchai Banmai | Cronus | normal | closed | Coke |  | - Share knowledge to Rex (EC01 Dev)
9 | ClassPath not found | EC02 | 2012-10-10 | 2012-10-10 | 1 | Config | Pinit Wongmaneerat | Niobe | normal | closed | Pong+ | none | - Connot start process - There is whitespace (' ', '\n', '\r') between ""
10 | Duplicate ret | E11 | 2012-10-09 | 2012-10-10 | 2 | BUG | Nopparat Ruangthong | Phoebe | high | closed | Tome | E11 v2.1.3 | - There is 2 ret attributes sending to EC02 - Removed by E11
11 | Cannot send/received Diam | ES06,ES07 | 2012-10-09 | 2012-10-10 | 8 | Knowledge | ALL | QA | normal | closed | Giraffe | none | - Incorrect version of diameter dict - Lack knowledge use of diam dict - Need to train?
12 | E03 Cloned Died when AF try to send alarm | E03 | 2012-10-10 | 2012-10-19 | 1 | BUG | Bhanumat Wiwatmaikul | Biz Live | normal | on progress | Pepsi |  | - When received message from AF, it crashed - Waiting for user re-test - Still waiting
13 | AF Received Reject Message | E03,E06 | 2012-10-10 | 2012-10-10 | 1 | AF | Bhanumat Wiwatmaikul | Biz Live | normal | closed | Pepsi | none | - Incorrect Error - Message sent form AF is not matched with Configuration - Train (by Coke) user how to use O&M part
14 | ecode = 2 from ES03 | EC02,ES03 | 2012-10-10 | 2012-10-10 | 1 | AF | Nopparat Ruangthong | Phoebe | low | closed | Tome | none | - Just surprise new error code from LDAP - Explain how to understand LDAP Error Code
15 | Incorrect Equinox Version | ALL | 2012-10-11 | 2012-10-16 | 4 | Process | ALL | ALL | high | closed | Tome | none | - User test on Equinox Old version - Waiting for Coke create the new package - Introduce command getVersion for user - Send package to TC to manage this consolidation - Create SVN repository for TC/Dev
16 | EC02 Not Support Thai Language | EC02 | 2012-10-12 | 2012-10-15 | 1 | UR | Thanuwat Sanla | Biz Live | normal | closed | Pong+ | EC02 v2.1.12 | - EC02 can't use thai language.
17 | No space left | ES00,E00 | 2012-10-12 | 2012-10-15 | 1 | Knowledge | Natdanai Bangnoy | TC | high | closed | Mig |  | - No space left problem on ES00,E00 - ES13 edb_purge message - Just cleanup disk
18 | Configuration confuse | ALL | 2012-10-12 | 2012-10-12 | 1 | Process | Kantipong Phairot | TC | normal | closed | Coke | none | - User don't read new templete configuration - sent them all configuration
19 | E01 start failed | E01 | 2012-10-12 | 2012-10-12 | 2 | Config | Nopparat Ruangthong | Phoebe | normal | closed | Tome | none | - Backup file was currupt. - 2 Line of single db entry
20 | Infinite Error at ES03 | ES03 | 2012-10-13 | 2012-10-13 | 1 | Knowledge | Pavaris Ajanaromwat | Phoebe | normal | closed | Tome | none | - When ES03 get error response from server, it goes to infinite loop - In ES03 log, it shows "bind resp return error" - Server doesn't allow client connection
21 | ES06 Crash | ES06 | 15/102012 | 2012-10-15 | 2 | BUG | Natkritta Khaminkhao | Niobe | normal | closed | Tome | dmp v1.0.16 ES06 v1.0.1 | - ES06 Crash if mandatory value in AVP differ from DICT - If it occurs more than 3, I will change priority to high. - This was fixed in dmp module version 1.0.16
22 | Diameter Processes don't support IPAddress | ES06,ES07 | 10/102013 | 2012-10-18 | 3 | UR | Arakin Rakchittapoke | AVP | normal | closed | Tome | ES06 v1.0.2 ES07 v1.0.9 | - Diameter cannot decode Address type without type - This is interim by change Address to OctetString in dict - Find the definition in RFC, but can't see any definition of Address without Address Family - Introduce new type named "IPAddress"
23 | E01 Backup File corrupt, but it doesn't | E01 | 2012-10-15 | 16/10.2012 | 1 | BUG | Nopparat Ruangthong | Phoebe | high | closed | Pup | E01 v.1.0.3 | - Cannot start E01 from backup file and "backup file corrupt" alarm is raised - There is duplicated line in backup file. (should raise another alarm) - Provisioning system doesn't allow to add duplication entry, however it can not see the differrence between data from backup file and new provisioning data.
24 | E01 can't return invoke | E01 | 2012-10-15 | 2012-10-15 | 1 | BUG | Daoyos Noikongka | Phoebe | normal | closed | Tome | E01 v.1.0.2 | - E01 can't return response invoke - invoke was returned in wrong place (EquinoxMessage)
25 | AF Received Message when timeout | E11 | 2012-10-16 | 2012-10-16 | 1 | Knowledge | Nopparat Ruangthong | Phoebe | normal | closed | Tome | none | - User doesn't understand why sometime he get returned message when timeout but sometime doesn't. - When timeout occurs, it will return the latest information put by AF
26 | ES03 abnormal terminate | ES03 | 2012-10-16 | 2012-10-16 | 1 | BUG | Nopparat Ruangthong | Phoebe | normal | closed | Tome | ES03 v1.1.1 | - Received non-wellform LDAP message, then crash - This can be fixed by server, ES03 should fix though - This problem is the same as issue 28 when the process try to free both parent and child memory section.
27 | Cannot find [Auth-Application-Id]avp with err[] | ES06 | 2012-10-16 | 2012-10-16 | 1 | Knowledge | Suporn Roddon | Niobe | normal | closed | Tome | none | - There is an error "Cannot find [Auth-Application-Id]avp with err[]" in log file - There is no "Auth-Application-Id" from AF
28 | ES05 Crash if xml is not well form | ES05 | 2012-10-16 | 2012-10-16 | 1 | BUG | Surasuk Kerdphon | QA | normal | closed | Mig | ES00 v1.0.6 | - ES05 crash when get non-well form XML from client. - It is a corruption in SF creation module when an error occurs, it will free memory both parent and child section. - Since SF_element_free will free all memory sections under parent, then we should not need to free memory on child section.
29 | ES00 Crash if found implicit closing tag in EquinoxRawData | ES00 | 2012-10-16 | 2012-10-19 | 2 | BUG | Bhanumat Wiwatmaikul Thanuwat Sanla | Biz Live Biz Live | normal | on progress | Mig |  | - EC02 generate this case when AF send empty data in text/plain mode. - This case is fixed by EC02 by insert white space if data is empty. - Anyway ES00 should handle this case, it should not to died at least.
30 | Error Destination not exist | ES00 | 2012-10-16 | 2012-10-16 | 1 | Config | Daoyos Noikongka | Phoebe | normal | closed | Coke | none | - User forgot to check connection between E00 and ES00 - IP-address & Port number already binding on another process - This problem can simply be fixed by setting correct connection IP-Address & Port number
31 | Ldap Response… | TM | 2012-10-16 | 2012-10-17 | 1 | Config | Pattanun Nisakul | QA | normal | closed | Giraffe | none | - Don't Understand Log in ES13 - ES13 already sent SF to AF but with new session - Need to add correlation plugin for ES13 (actually every server)
32 | ES13 Reconnect to E00 | ES13 | 2012-10-09 | 2012-10-17 | 1 | Config | Natdanai Bangnoy | TC | normal | closed | Tome | none | - Don’t know why ES13 try to reconnect to E00 if there are more than 2 E00 hosts. - An "watchdog timeout" alarm is also raised. - In configuration, the housekeeper_interval is grater than watchdog_interval. - In our process, it should check that the housekeeper_interval have to be the lowest interval.
33 | ES03 don't return invoke | ES03 | 2012-10-17 | 2012-10-17 | 1 | BUG | Pawarich Ajanaromwat | Phoebe | normal | closed | Tome | ES03 v1.1.0 | - User sent invoke id but ES03 don’t return response. - The process will return invoke only if message is LDAP extended. - Need to add the feature to support search, add, modify, delete
34 | ES07 Crash when received Diameter Request | ES07 | 2012-10-17 | 2012-10-17 | 1 | BUG | Theerawut Kingpaiboon | Biz Live | normal | closed | Tome | dmp v1.0.16 ES07 v1.0.8 | - It crashed when received the request that differ from DICT - This is fixed by rebuild process with new dmp version
35 | Cannot send data to ES06 | ES06 | 2012-10-17 | 2012-10-17 | 1 | Config | Pawarich Ajanaromwat | Phoebe | normal | closed | Tome | none | - Can't send data to ES06 - Configure incorrect SF port
36 | Cannot send Diameter by ES06 | ES06 | 2012-10-17 | 2012-10-17 | 1 | Knowledge | Pawarich Ajanaromwat | Phoebe | normal | closed | Tome | none | - ES06 can't send diameter to server - Developer don't know how to set the value in AVP
37 | Cannot query E01 | E01 | 2012-10-18 | 2012-10-18 | 1 | Knowledge | Surasuk Kerdphon | QA | normal | closed | Tome | none | - E01 Return no such object to application. - AF send incorrect key to E01.
38 | AF cannot get response | EC02 | 2012-10-18 | 2012-10-18 | 7 | BUG | Pawarich Ajanaromwat Pinit Wongmaneerat Ploynatcha Deatanuntanarat Athaporn Kaewngam | Phoebe Niobe QA QA | high | closed | Tome | E11 v2.2.1 | - Message is dropped by E11 since it was slave copy in database. - Something wrong in master/slave negotiate - My eyes and my back are hurt but I finally found the E11 use the master status from database to check condition. - I thought I was sick.
39 | ES07 process down | ES07 | 2012-10-18 | 2012-10-18 | 1 | Process | Daoyos Noikongka | Phoebe | normal | closed | Tome | none | - Fixing ES07 dict by Tome (Stop Process) - There are many independent applications on this machine why?
40 | ES00 Spin | ES00 | 2012-10-18 | 2012-10-18 | 1 | AF | Daoyos Noikongka | Phoebe | normal | closed | Mig | ES00 v1.0.7 | - CPU load process ES00 100% and can't forward message from ES03 - It is a bug in ES00 but actually this case occurs when AF didn't send "to" parameter in EquinoxRawData. - Since it is bug on ES00, ES00 shall be fixed eigther. - Thanks to user to help us find this bug.
41 | Exception at EC02 | EC02 | 2012-10-18 | 2012-10-19 | 1 | Knowledge | Natkritta Khaminkhao | Niobe | normal | closed | Tome | none | - EC02 crash and exception when received diameter message from ES07 - There is something wrong in User-Equipment-Info-Value - User thinks that this problem occur after upgraded Equinox - Try to find log at ES07 but we can't see anything - We found that we were looking into incorrect log - 2 words from user "hae hae"
42 | Get new instance when timeout | E11 | 2012-10-19 | 2012-10-19 | 1 | Knowledge | Daoyos Noikongka | Phoebe | normal | closed | Tome | none | - User don't know why after sent the message, AF received the new instance from E11 - Message is loop from ES06 to Another App and come back to ES07 with new session
43 | Connection Refuse at ES00 | ES00 | 2012-10-19 | 2012-10-19 | 8 | Knowledge | Nopparat Ruangthong Theerawut Kingpaiboon Aroonwadee Promma Pattanun Nisakul | Phoebe | normal | closed | Tome | none | - AF didn't get response from External, user good try to look at ES00 and found that there was an "connection refuse" error. - Got the same error when try to telnet EC02 port - If user look into EC02 log, user will see the exception log in JAVA code himself. it will explain why it got error and died.
44 | "IDLE::" wording in instance data | EC02 | 2012-10-19 | 2012-10-19 | 1 | Knowledge | Surasak Thongin | Phoebe | normal | closed | Tome | none | - User see unexpected data in EquinoxInstance - Why EC02 have to put any other data in EquinoxInstance itself? - This area should be controlled by AF, shouldn't it? - That data is state and special delimiter. - EC02 separates state and instance to each attribute in JAVA. However it merges this data together after AF responses the message to platform. - Why not?
45 | An exception in EC02 | EC02 | 2012-10-19 | 2012-10-19 | 5 | BUG | Nopparat Ruangthong Pawarich Ajanaromwat Sedtawut Arunsri | Phoebe Phoebe Phoebe | normal | on progress | Pong+ | EC02 v2.1.13 | - There are many exception in EC02. - This is because some people still use the old version of EC02 - I can deny the responsibility that there is some bug which EC02 has to fix it.
46 | Unknown message from EC02 | EC02 | 2012-10-19 | 2012-10-19 | 1 | Knowledge | Natthaporn Pakdee | QA | normal | closed | Tome | none | - From log at ES00 we found that there was a timeout event sent to AF - EC02 sent back the unknown message to ES00, cause an error at ES00 log - When We check at EC02 log there were a lot of exception caused by AF - AF cann't handle timeout event from equinox - However EC02 shall fix this message too.
47 | Cannot start ES05 | ES05 | 2012-10-22 | 2012-10-22 | 1 | Config | Kantipong Phairot | TC | normal | closed | Tome | none | - Can not start ES05 process - There was an error port already in used - Something wrong in configuration - There were many APP run on this machine, and used the same port
48 | E01 return not well form xml when error | E01 | 2012-10-22 | 2012-10-22 | 1 | BUG | Syoomphoo Kongsook | Metis | normal | closed | Pup | E01 v1.0.4 | - It seems double quote is missing in return xml message when result code is not equal to 0
49 | EC02 Pass NULL object to AF | EC02 | 2012-10-22 | 2012-10-22 | 1 | AF | Nopparat Ruangthong | Phoebe | normal | closed | Tome | none | - EC02 Crash after sent Object to AF - AF found that the Object passed by EC02 is null - EC02 passed String to ExtractInstance and wait for Object from this method - EC02 got null Object from ExtractInstance method created by AF… - Something wrong in Object decoder in AF
50 | AF cannot get request from ES07 | ES07 | 2012-10-22 | 2012-10-22 | 1 | Knowledge | Aroonwadee Promma | Biz Live | normal | closed | Tome | none | - ES07 didn't send request message to AF - An error was found at ES07 log - Error indicate incorrect command code - Common code is not found in Dict
51 | Where is my E11? | E11 | 2012-10-22 | 2012-10-22 | 1 | Config | Chitti Piriyabenchawat | - | normal | closed | Tome | none | - Cannot start E11 process - E11 configuration was missing
52 | EC02 cannot get the input message | EC02 | 2012-10-22 | 2012-10-22 | 1 | Config | Chitti Piriyabenchawat | - | normal | closed | Tome | none | - ES00 already sent the message to EC02 but no any response from it - In EC02 log, the alarm cann't find AF class is raised - The AF class configuration in EC02 is incorrect
53 | Response message from ES06 is not sent to ES00 | ES06 | 2012-10-22 | 2012-10-22 | 1 | AF | Natkritta Khaminkhao | Niobe | normal | closed | Tome | none | - ES06 doesn't send response message to ES00 - There is a timeout occur at E11 log - AF send timeout 0 for this case - Should I change E11 to support fast response when timeout = 0?

## Support Case 2013
| Last updated: | 2013-11-26
Category : AF, Bug, Config, Process, Knowledge, Taining, UR
Priority : Low, Normal, High
Status : Opened, Gathering, On process, Closed
Issue ID. | Issue | EQX Process | Register Date | Target Date | Occurs | Category | Requester/Initiator | Group | Priority | Status | Escalated | Fixed in version | Detail | Defect ID
IID0713004 | [PCRF] AF log retry | Unknown | 2013-07-30 | 2013-07-31 | 1 | AF | Pawarich Ajanaromwat Pinit Wongmaneerat | Niobe | Normal | Closed | Pepsi | none
IID0813003 | [SMSCTF] Fail to verify AF configuration | EC00 | 2013-08-01 | 2013-08-02 | 1 | AF | Rochana Macharoen | Niobe | Normal | Closed | Fern, Pepsi, Tome | none | -[Thu Aug 1 17:08:35 ICT 2013] Start EC00 for 0 (0) for SMSCTF... [ERROR¦17:08:35¦4025¦sfconfig.c¦SF_config_find_element¦241¦value buffer may not big enough FATAL¦17:08:35¦4025¦EC00.c¦config_load_cold¦2040¦Fail to verify AF configuration] [ERROR¦20130801¦17:08:35¦process_verify¦Process was started incorrectly.] Do you want continue, but your system may not work properly?(y/n) is occured while attempting to start EC00 because of verification of configuration failed. -This issue can be fixed by increase buffer size. - Road map >> developer guide
IID0813006 | [OFF] Wording "N/A" found in EquinoxRawData | EC02 | 2013-08-02 | 2013-08-06 | 1 | AF | Cherdsit Thongsongsuk | TC | Normal | Closed | Pong, Fern | none | - <EquinoxRawData orig="N/A" to="OFF.ES00" invoke="N/A" name="N/A" ctype="N/A" type="request" ret="4">
IID0813011 | [OFF] EC02 has 2 EquinoxMassage | EC02 | 2013-08-08 | 2013-08-09 | 1 | AF | Ploy Sae-Tung | QA | Normal | Closed | Aof | none | - Equinox message duplicate (Roadmap protection eqxmeassag).
IID0813017 | Sol10, verify config is pass but process is still down | EC02 | 2013-08-20 | 2013-08-20 | 1 | AF | Pinit Wongmaneerat | Pheobe | Normal | Closed | Pong | none | -NullPointerException in AF
IID0813023 | ES00 does not received message from AF | ES00 | 2013-08-23 | 2013-08-26 | 1 | AF | Thanuwat Sanla | Façade Bizlogic | Normal | Closed | Fern | none | -ERROR¦09:22:01¦9771¦ES00.c¦housekeeper¦3738¦HTTP wait timedout while in state [STATE_WAITING] INFO¦09:22:01¦9771¦ES00.c¦h_clnt_close¦1475¦Will retry this message ERROR¦09:22:01¦9771¦ES00.c¦h_clnt_close¦1479¦Too many retries -AF must response on (timeout = “10” )
IID0813025 | [OFF] XML DATA has " ' " | testamentor | 2013-08-30 | 2013-08-30 | 1 | AF | Ploy Sae-Tung | QA | Normal | Closed | Aof | none | - XML data from AF has " ' " (single qout)
IID0913010 | [PCRF] Problem EC02 or AF? | EC02 | 2013-09-20 | 2013-09-20 | 1 | AF | Pawarich Ajanaromwat | Pheobe | High | Closed | Pong | none | -An error occurred in E00 log (Distination not exist) -This issue is fixed by AF
IID0913012 | 400 Bad Request | ES05 | 2013-09-23 | 2013-09-23 | 1 | AF | Oranong Rorhun, Taksina Thamintong | QA | Normal | Closed | Fern | none | -ERROR¦18:12:57¦13891¦ES05.c¦hs_sess_decode¦3731¦400 Bad Request: Server could not interpret or understand the request, probably syntax error in the request message. [session_no:0] is occurred in ES05 log -receive "POST HTTP/1.1" header from BDG. It must be "POST / HTTP/1.1"
IID0913013 | Content-Length: not found | ES05 | 2013-09-23 | 2013-09-23 | 1 | AF | Oranong Rorhun, Taksina Thamintong | QA | Normal | Closed | Fern | none | -ERROR¦18:40:25¦13891¦ES05.c¦hs_sess_decode¦3739¦Session(0), HTTP Content-Length: not found - Data[POST / HTTP/1.1 -receive "Content-length" header from BDG. It must be "Content-Length"
IID1013005 | receive ecode="400" with no body data | ES04 | 2013-10-03 | 2013-10-03 | 1 | AF | Oranong Rorhun | QA | Normal | Closed | Aof | none
IID0713003 | LDAP write timedout while in state [STATE_READY] | ES03 | 2013-07-30 | 2013-07-30 | 1 | Bug | Siwanat Ponkhun | TC | Normal | Closed | Tome | 1.3.x | -ES03 V1.2.2 will waiting for keepalive from server, If there is no response, ES03 will be disconnected from server. -This issue can be fixed by update ES03 version 1.3.x.
IID0813005 | [MMSDP] Memory leak | E04 | 2013-08-02 | 2013-08-06 | 1 | Bug | Cherdsit Thongsongsuk | TC | High | Closed | Pepsi | equinox-1.2.0-04-solaris.patch.zip | -This issue can be fixed byupgrade patch.
IID0813016 | [SMF] EC02 core dumped | EC02 | 2013-08-19 | 2013-08-19 | 1 | Bug | Wilinda Khamdee | TC | High | Closed | Pepsi | EC02 v.3.1.3 | -EC02 Buffer overflow. (DEBUG log) -This issue already fixed on new version
IID0813018 | [PCRF] Group[0] not found!!! | E00 | 2013-08-21 | 2013-08-26 | 1 | Bug | Pawarich Ajanaromwat | Pheobe | High | Closed | Pepsi | EC02 v.3.1.3 | -WARNING¦14:01:58¦10481¦E00.c¦session_decode¦1931¦Group[0] not found!!! ERROR¦14:05:09¦10481¦E00_service.c¦add_instance¦187¦Group [0] Instance[1] had used STATUS[1] is occurred in E00 log because of EC02 core dumped and then E00 paused.
IID0813020 | [PCRF] EC02, E00 core dumped | EC02 | 2013-08-22 | 2013-08-26 | 1 | Bug | Kantipong Phairot | TC | High | Closed | Pepsi | EC02 v.3.1.3, Equinox release 1.3.0 | -EC02 Buffer overflow. -E00 Retry... -This issue already fixed on new version
IID0813021 | [ENUMFE3G401][MMS] Equinox process hang and uossi do not send alarm | All | 2013-08-22 | 2013-08-22 | 1 | Bug | Witthawat Pradit | TS | High | Closed | Fern | none | -ENUMFE use E00 version 1.0.3.8, E11 version 1.0.0.1, ES00 version 1.0.5.10, ES02 version 1.0.0.0, ES09 version 1.0.0.1 -This version has issue about shared memory which affect the performance of kernel -This issue can be fixed by reboot server when an error occured (interim) or upgade Equinox and AF, this issue is already fixed in Equinox v.x.x.x
IID0813022 | E11, ES00, ES10 core dumped on Apollo (Solaris) | E11, ES00, ES10 | 2013-08-22 |  | 1 | Bug | Phatcharee Sittisanwattanachai | Pheobe | Normal | On progress | Fern,Tome
IID0813030 | [SRFP] ES10 core dumped | ES10 | 2013-08-26 | 2013-08-26 | 1 | Bug | Rattached Janketwiroj | QA | Normal | Closed | Fern | none | -INFO¦11:03:23¦27879¦ES10.c¦fmon_loop¦2908¦Process 18618 abnormal termination on signal [Segmentation fault] (core dumped) INFO¦11:03:23¦27879¦ES10.c¦fmon_loop¦2919¦Will restart process after (10) second INFO¦11:03:35¦27879¦ES10.c¦fmon_loop¦2849¦Restart process is occurred in ES10 log - this issue can be fixed by upgrade ES10 new version
IID0913004 | [SMF] EC02 application error handling | EC02 | 2013-09-09 | 2013-09-10 | 1 | Bug | Napalai Wicha | QA | Normal | Closed | Pong | EC02 v.3.1.3 | -EC02 generate EquinoxRawData with empty “to.” <EquinoxRawData to="" ret="2" invoke="default_invoke" type="response" > [[TIMEOUT]]</EquinoxRawData> -This issue is already fixed on EC02 version 3.1.3
IID0913006 | [PCRF] EC02 core dumped | EC02 | 2013-09-16 | 2013-09-23 | 1 | Bug | Napatsawan Petchkong | TS | High | Closed | Pepsi, Fern | EC02 v.3.1.3 | -EC02 Buffer overflow. -This issue already fixed on EC02 version 3.1.3
IID0913008 | [INGW-ETOPUP] incorrect EquinoxRawData structure, use val | EC02 | 2013-09-17 | 2013-09-17 | 1 | Bug | Siwanat Ponkhun, Wanchai Mukdapun | TC | Normal | Closed | Aof | EC02 v.3.1.3 | - incorrect EquinoxRawData structure, use val
IID0913009 | [OCFHK] ES03 core dumped | ES03 | 2013-09-19 | 2013-09-25 | 1 | Bug | Pawarich Ajanaromwat | Pheobe | Normal | Closed | Pepsi, Aof | ES03 v.1.3.2
IID0913014 | eqx VERSION 1.9.2 บน Solaris ไม่สามารถใช้คำสั่ง status กับ EC02 | eqx | 2013-09-24 | 2013-09-24 | 1 | Bug | Kulrojh Roongruangpitthayakul | Pheobe | Normal | Closed | Fern, Pepsi | none | -upgrade eqx
IID0913015 | testamentor CDATA | testamentor | 2013-09-24 | 2013-09-24 | 1 | Bug | Oranong Rorhun | QA | Normal | Closed | Aof | none | -increse CDATA buffer
IID0913016 | ES04 ไม่ ret 0, 4, 10 บาง version | ES04 | 2013-09-24 | 2013-09-24 | 1 | Bug |  | QA | Normal | Closed | Aof | none | -upgrade ES04 new version
IID0913017 | injector ไม่มี default ecode ของ smpp | testamentor | 2013-09-26 | 2013-09-26 | 1 | Bug | Oranong Rorhun | QA | Normal | Closed | Aof | none | -this issue is already fixed
IID1013001 | [OCFHK] ES03 core dumped | ES03 | 2013-10-03 | 2013-10-04 | 1 | Bug | Pawarich Ajanaromwat | Pheobe | Normal | Closed | Aof | none | - extend
IID1013002 | [OCF] ES07 memory leak | ES07 | 2013-10-03 |  | 1 | Bug | Nattawat Ujjin | VOS1 | High | On progress |  |  | - restart ทั้ง equinox แล้วหาย แต่จะต้องตรวจสอบต่อ
IID1013003 | [PCRF] E11, EC02 core dumped | E11, EC02 | 2013-10-03 | 2013-10-04 | 1 | Bug | Natdanai Bangnoy | TC | High | Closed | Fern, Tome, Pepsi | EC02 v.3.1.3, Equinox release 1.3.0 | - E11 : message over flow - EC02 : resource management
IID1013004 | testamentor CDATA | testamentor | 2013-10-03 | 2013-10-03 | 1 | Bug | Oranong Rorhun | QA | Normal | Closed | Aof | none | -increse CDATA buffer
IID1013006 | testamentor multiraw |  | 2013-10-03 | 2013-10-03 | 1 | Bug | Oranong Rorhun | QA | Normal | Closed | Aof | none | -An error ocuured while testamentor receive multi rawdata - this issues is fixed by update new corralate
IID1013009 | testamentor ค่า VAR random ในเวลาเดียวกัน ได้เลขเหมือนกัน | testamentor | 2013-10-07 | 2013-10-07 | 1 | Bug | Warin Permpul | QA | Normal | Closed | Aof | none
IID1013010 | [INGW-ETOPUP] HTTP write timedout while in state [STATE_WRITING] | ES00 | 2013-10-09 | 2013-10-09 | 1 | Bug | Wanchai Mukdapun | TC | High | Closed | Fern, Aof, Pepsi | none | -ERROR¦07:35:56¦19250¦ES00.c¦housekeeper¦3723¦HTTP write timedout while in state [STATE_WRITING] INFO¦07:35:56¦19250¦ES00.c¦h_clnt_close¦1473¦Will retry this message -Road map : change from
IID1013012 | [BDG] SSMPP enum >= 128 ฝั่งรับจะเห็นติดลบ | ES10, ES11 | 2013-10-09 | 2013-10-09 | 1 | Bug |  | Niobe | Normal | Closed | Aof | none | -upgrade ES10, ES11
IID1013014 | Cannot start EC02 (equinox package 1.3.0) | EC02 | 2013-10-10 | 2013-10-10 | 1 | Bug | Pornpimol Gengmon | Aware | Normal | Closed | Fern, Pong | none | -[root@localhost jdk1.6.0_38]# /opt/equinoxAS/bin/EC02 /opt/equinoxAS/bin/EC02: error while loading shared libraries: libjvm.so: cannot open shared object file: No such file or directory
IID1013015 | [OCF] Redundancy message | EC02 | 2013-10-11 |  | 1 | Bug | Napatsawan Petchkong | TS | High | On progress | Fern, Pepsi, Pong
IID1013016 | eqx cannont start keyword "ES" in app name | eqx | 2013-10-11 | 2013-10-11 | 1 | Bug | Pornpimol Gengmon | Aware | Normal | Closed | Fern, Pepsi | none | -upgrade eqx
IID1013018 | [PCRF] ES00 core dumped | ES00 | 2013-10-15 |  | 1 | Bug | Cherdsit Thongsongsuk | TC | High | On progress | Aof
IID1013019 | [OFF] EC02 core dumped | EC02 | 2013-10-15 |  | 1 | Bug | Cherdsit Thongsongsuk | TC | High | On progress | Pong
IID1013020 | [OCF] ES07 correlate | ES07 | 2013-10-16 | 2013-10-16 | 1 | Bug | Napalai Wicha | QA | High | Closed | Aof | none
IID1013023 | [SMSCTF] ES07 session | ES07 | 2013-10-17 | 2013-10-17 | 1 | Bug |  | Niobe | Normal | Closed | Aof | none | -this issue is already fixed in new version
IID1013025 | [BDG] sm_message ติดลบ | ES10 | 2013-10-17 | 2013-10-17 | 1 | Bug | Oranong Rorhun | QA | Normal | Closed | Aof | none
IID1013028 | injector - send and receive message size overflow | testamentor | 2013-10-29 | 2013-10-29 | 1 | Bug |  | QA | Normal | Closed | Aof | none
IID1013029 | injector - xml parser (core dumped) | testamentor | 2013-10-29 | 2013-10-29 | 1 | Bug |  | QA | Normal | Closed | Aof | none
IID1013030 | [OCF] receive wrong session (correlate) | ES07 | 2013-10-29 | 2013-10-29 | 1 | Bug |  | QA | Normal | Closed | Aof | none | -upgrade correlate
IID1013031 | [OCFHK] process down when receive message with correlate | ES05 | 2013-10-30 | 2013-10-30 | 1 | Bug | Pawarich Ajanaromwat | Pheobe | Normal | Closed | Aof | none | -upgrade new version
IID1013032 | [OCFHK] correlate cannot parse "&amp;" | ES05 | 2013-10-30 | 2013-10-30 | 1 | Bug | Pawarich Ajanaromwat | Pheobe | Normal | Closed | Aof | none | -upgrade correlate
IID1013033 | [OCFHK] purge is occurred when receive more traffic | ES05 | 2013-10-30 | 2013-10-30 | 1 | Bug | Pawarich Ajanaromwat | Pheobe | Normal | Closed | Aof | none | -upgrade new version
IID1113005 | ES10 core dumped | ES10 | 2013-11-15 | 2013-11-16 | 1 | Bug | Yawd Saiveaw | Aware | Normal | Closed | Aof | none
IID1113006 | ES11 core dumped | ES11 | 2013-11-15 | 2013-11-16 | 1 | Bug | Yawd Saiveaw | Aware | Normal | Closed | Aof | none
IID1113008 | EC02 core dumped around 4 am everyday | EC02 | 2013-11-21 |  | 1 | Bug | Yawd Saiveaw | Aware | High | On progress
IID1113009 | ES05 choose wrong E11 | ES05 | 2013-11-21 | 2013-11-22 | 1 | Bug | Wilinda Khamdee | TC | Normal | Closed | Tome, Fern
IID1113010 | [SMF] timeout is incoming with ret="2" | ES04 | 2013-11-22 | 2013-11-26 | 1 | Bug | Manosate Pipatpatama | Niobe | Normal | Closed | Aof, Fern |  | ES05 v.1.5.10 ERROR¦12:16:30¦28070¦ES04.c¦housekeeper¦6073¦HTTP wait timedout while in state [STATE_WAITING] ERROR¦12:16:30¦28070¦ES04.c¦h_clnt_close¦1822¦Reject Message (1:SMF.ES05.SMFOCF.0), HTTP connection closed while process DEBUG¦12:16:30¦28070¦ES04.c¦sf_reply_msg¦4779¦Reply SF to [SMF.E11.0]
IID1113011 | E00 core dumped | E00 | 2013-11-22 |  | 1 | Bug | Wilinda Khamdee | TC | Normal | On progress
IID1113012 | E11 core dumped | E11 | 2013-11-22 | 2013-11-22 | 1 | Bug | Wilinda Khamdee | TC | Normal | Closed | Tome, Fern
IID0713002 | Connection reset by peer in state REGISTER | E00, ES04 | 2013-07-30 | 2013-07-30 | 1 | Config | Manosate Pipatpatama | Niobe | Normal | Closed | Fern | none | - ERROR¦10:42:58¦18171¦ES04.c¦sf_process¦3415¦SF_clnt_loop return error [recv return error [Connection reset by peer] in state [STATE_REGISTER]] ERROR¦10:43:08¦18171¦ES04.c¦housekeeper¦4027¦SF_clnt_loop return error [recv return error [Connection reset by peer] in state [STATE_REGISTER]] is occurred in ES04 log because of E00 received "Too many sessions" - This issue can be fixed by increase MaxSession in client process configuration.
IID0813002 | [SMF] ec02 internal error | EC02 | 2013-08-01 | 2013-08-01 | 1 | Config | Manosate Pipatpatama | Niobe | High | Closed | Fern | none | - ERROR¦16:53:32¦ECThread-006¦controller.EC02Controller.java¦ec02.controller.EC02Controller¦process¦100¦ec02 internal error is occurred in EC02 log because of missing JavaLibrary (gson-2.2.2.jar) -This issue can be fixed by add <JavaLibrary value="gson-2.2.2.jar" /> in EC02 Client Proceess Configuration
IID0813004 | [SMSCTF] Dictionary was not found | ES10 | 2013-08-01 | 2013-08-02 | 1 | Config | Rochana Macharoen | Niobe | Normal | Closed | Fern, Pepsi, Tome | none | -[Thu Aug 1 17:19:23 ICT 2013] Start ES10 for SGSCP (0) for SMSCTF... [ERROR¦17:19:23¦4188¦ES10.c¦config_load_cold¦2217¦Dictionary was not found] [ERROR¦20130801¦17:19:23¦process_verify¦Process was started incorrectly.] Do you want continue, but your system may not work properly?(y/n) -This issue can be fixed by add dict="/opt/equinox/conf/smpp.spec" (full path) in Client Process Cold Configuration and add smpp.spec to /opt/equinox/conf
IID0813008 | [SMSCTF] AVP code [874] not found | ES06 | 2013-08-07 | 2013-08-07 | 1 | Config | Rochana Macharoen | Niobe | Normal | Closed | Aof | none | -ERROR¦17:18:49¦29480¦ES06.c¦dc_process¦2575¦DMP_clnt_loop return error [AVP code [874] not found] is occurred in ES06 log because of AVP code [874] set vendor-bit="may" vendor-id="TGPP" -This issue can be fixed by change value of vendor-bitin ES06 dictionary to "must"
IID0813010 | ES04 INJ | EC02 | 2013-08-08 | 2013-08-08 | 1 | Config | Ploy Sae-Tung | QA | Normal | Closed | Aof | none | - Set permanence = no, for ES04 case injector. This case in order to protect connection resetting.
IID0813012 | EC02 configuration | EC02 | 2013-08-08 | 2013-08-08 | 1 | Config | Pawarich Ajanaromwat | Pheobe | Normal | Closed | Pong | none | - Not found message, config debug in order to open info log level.
IID0813013 | [OFF] (loadtest) purge | ES07 | 2013-08-13 | 2013-08-13 | 1 | Config | Cherdsit Thongsongsuk | TC | Normal | Closed | Aof, Fern | none
IID0813024 | AVP Error-Message [281] must not set mandatory flag | ES06 | 2013-08-30 | 2013-08-30 | 1 | Config | Natkritta Khaminkhao | Niobe | Normal | Closed | Fern | none | AVP Error-Message [281] must not set mandatory flag
IID0813027 | Write log incomplete | E06 | 2013-08-26 | 2013-08-26 | 1 | Config | Manosate Pipatpatama | Niobe | Normal | Closed | Fern | none | - WARNING¦10:00:01¦30176¦E06.c¦af_log_write¦958¦Write log incomplete writen[0] buffer_len[8] is occured in E06 log
IID0813028 | Destination not exist | RA | 2013-08-26 | 2013-08-26 | 1 | Config | Manosate Pipatpatama | Niobe | Normal | Closed | Fern | none | -ERROR¦10:55:10¦2509¦ES05.c¦sf_recv_msg¦1894¦Invalid type [request] DEBUG¦10:55:10¦2509¦ES05.c¦sf_reply_msg¦1664¦Reply SF to [SMF_OSRAR_0.E11.1] DEBUG¦10:55:10¦2509¦ES05.c¦get_equinox_msg_attr¦1776¦timeout not found DEBUG¦10:55:10¦2509¦ES05.c¦sf_recv_msg¦1845¦Extracted equinox: from[SMF_OSRAR_0.E00.x.0], via[SMF_OSRAR_0.E11.1], session[1:SMF_OSRAR_0.ES05.OSRAR.0], timeout[0], ret[2], diag[Destination not exist] is occured in ES05 log and ERROR¦10:54:40¦2286¦E00.c¦session_new_msg¦1565¦Session (13), service [SMF_OSRAR_0.E11.1] not found ERROR¦10:54:40¦2286¦E00.c¦session_new_msg¦1576¦####### REJECT ret [2] diag [Destination not exist] is occured in E00 log
IID0813029 | Destination not exist | ES07 | 2013-08-26 | 2013-08-26 | 1 | Config | Manosate Pipatpatama | Niobe | Normal | Closed | Fern | none | -ERROR¦11:17:26¦4026¦E00.c¦session_new_msg¦1565¦Session (17), service [SMF_OSRAR_0.ES07.OCF_SUK1] not found ERROR¦11:17:26¦4026¦E00.c¦session_new_msg¦1576¦####### REJECT ret [2] diag [Destination not exist] is occured in E00 log
IID0813031 | [SMF] E00 queue | Unknown | 2013-08-26 | 2013-08-27 | 1 | Config | Wilinda Khamdee | TC | High | Closed | Pepsi | none
IID0913002 | [INGW-ETOPUP] EC02 | EC02 | 2013-09-04 | 2013-09-04 | 1 | Config | Kulrojh Roongruangpitthayakul | Pheobe | Normal | Closed | Pong | none | - set EC02 full path link
IID0913003 | ES13 Register | ES13 | 2013-09-05 | 2013-09-05 | 1 | Config |  | QA | Normal | Closed | Aof | none | -ERROR¦11:23:53¦24772¦ES13.c¦housekeeper¦4457¦SF_clnt_loop return error [Timedout while in state [STATE_REGISTER]] ERROR¦17:04:37¦24772¦ES13.c¦housekeeper¦4457¦SF_clnt_loop return error [Watchdog timedout while in state [STATE_READY]] set HousekeeperInterval value less than other Interval
IID0913007 | [INGW-ETOPUP] Unexpected data read | ES04 | 2013-09-17 | 2013-09-17 | 1 | Config | Siwanat Ponkhun, Wanchai Mukdapun | TC | Normal | Closed | Aof | none | - Unexpected data read in state [STATE_READY] - this issue can be fixed by set permanence="no"
IID1013007 | [SRFC] Empty session message is not allowed, this message will be dropped!!! | E11 | 2013-10-08 | 2013-10-09 | 1 | Config | Aroonwadee Promma | Facade | Normal | Closed | Tome, Aof | none | -WARNING¦09:56:02¦30027¦E11.c¦sf_recv_msg¦8349¦Empty session message is not allowed, this message will be dropped!!! -upgrade lib correlate
IID1013008 | [BDG] SMPP enum ใน dict ไม่เกิน 15 ตัว | ES10, ES11 | 2013-10-07 | 2013-10-07 | 1 | Config |  | Niobe | Normal | Closed | Aof | none | -change data in dictionary
IID1013011 | [SRFP] EC02 configuration | EC02 | 2013-10-09 | 2013-10-09 | 1 | Config | Phadet Samanaviriya | Cronos | Normal | Closed | Fern | none | -
IID1013026 | [OFF] Too many session | EC02 | 2013-10-28 | 2013-10-28 | 1 | Config | Ploy Sae-Tung | QA | Normal | Closed | Aof | none
IID1013027 | [OCF] Timeout in state waiting | ES00 | 2013-10-28 | 2013-10-28 | 1 | Config |  | QA | Normal | Closed | Aof | none
IID1113004 | [SRFC] Destination not exist | E00 | 2013-11-08 | 2013-11-08 | 1 | Config | Cherdsit Thongsongsuk | TC | Normal | Closed | Fern | none
IID0813007 | E01 provisioning | E01 | 2013-08-06 | 2013-08-16 | 1 | Knowledge | Puunyapat Rakmun | SPOC2 | Normal | Closed | Putt | none | - Provisioning duplicate key with difference data
IID0913001 | NO_SUCH_OBJECT | E01 | 2013-09-02 | 2013-09-03 | 1 | Knowledge | Kittisak Srina | Niobe | Normal | Closed | Tome | none | -This case is fixed, since user doesn’t know about NEAREST and DEF feature on E01.
IID0913011 | Configuration E01 | E01 | 2013-09-23 | 2013-09-23 | 1 | Knowledge | Kittisak Srina | Niobe | Normal | Closed | Phutt | none
IID0913018 | injector ES11 ต้องส่ง oid="[system_id]" | testamentor | 2013-09-26 | 2013-09-26 | 1 | Knowledge | Oranong Rorhun | QA | Normal | Closed | Aof | none
IID0913019 | ES10, ES11 system_id > 15 characters, system_password > 8 characters | testamentor | 2013-09-26 | 2013-09-26 | 1 | Knowledge | Oranong Rorhun | QA | Normal | Closed | Aof | none
IID0913020 | C-Octet ต้องใส่ 0x.. | testamentor | 2013-09-26 | 2013-09-26 | 1 | Knowledge | Oranong Rorhun | QA | Normal | Closed | Aof | none
IID0913021 | ES06, ES10 ขา response ต้องใส่ .instance ที่ dest เพื่อให้ตัด string session ถูก | testamentor | 2013-09-26 | 2013-09-26 | 1 | Knowledge | Oranong Rorhun | QA | Normal | Closed | Aof | none
IID0913032 | shmget | Unknown | 2013-09-30 | 2013-09-30 | 1 | Knowledge | Chayada Siriphakhamongkhon | Niobe | Normal | Closed | Aof | none | - eqx clrmem
IID1013013 | [OCFHK] พอปรับเวลาเครื่องแล้วโดนตัด connection PUASE ไม่หาย | ES03, ES06 | 2013-10-10 | 2013-10-10 | 1 | Knowledge | Ploy Sae-Tung | QA | Normal | Closed | Aof | none | -reatart process
IID1013021 | [SRFP] E01 key | E01 | 2013-10-16 | 2013-10-16 | 1 | Knowledge | Phadet Samanaviriya | Cronos | Normal | Closed | Pepsi | none
IID1013022 | [SRFP] E01 timeout | E01 | 2013-10-16 | 2013-10-16 | 1 | Knowledge | Ploy Sae-Tung | QA | Normal | Closed | Pepsi | none
IID1013024 | [INGW-ETOPUP] recv return error [Connection reset by peer] | ES05 | 2013-10-17 | 2013-10-17 | 1 | Knowledge | Wanchai Mukdapun | TC | Normal | Closed | Fern | none | - ERROR¦07:02:17¦19397¦ES05.c¦hs_sess_read¦2954¦Session(0), recv return error [Connection reset by peer]
IID1113007 | [MMSDP] New E04 have stat group | E04 | 2013-11-18 | 2013-11-18 | 1 | Knowledge | Chayada Siriphakhamongkhon | Niobe | Normal | Closed | Pepsi | none
IID0713001 | EC02 library is not compatible with EC02 server | EC02 | 2013-07-24 | 2013-07-24 | 1 | Process | Chayada Siriphakhamongkhon | Niobe | Normal | Closed | Fern, Pong | none | - FATAL¦16:05:51¦10096¦JavaInterface.cpp¦callECMethodHandle¦389¦Error Processing in java WARNING¦16:05:51¦10096¦WorkerThread.cpp¦executeThis¦151¦callECMethodHandle return error (-1) is occurred in EC02 log because of EC02 library (ec02_library_V3.1.0.jar) is not compatible with EC02 server (V.3.1.2)
IID0813001 | [MMSDP] Cannot forcestop EC02 | EC02 | 2013-08-01 | 2013-08-01 | 1 | Process | Chayanan Suparcha | VOS2 | Normal | Closed | Pepsi | none | -ld.so.1: EC02: fatal: libjvm.so: open failed: No such file or directory is occurred while attemping to stop EC02 because of .profile of package equinox-1.2.0-solaris.pkg doesn't have equinoxAS, so LD_LIBRARY_PATH does not exist. -This issue can be fixed by copy LD_LIBRARY_PATH from .bash_profile (LD_LIBRARY_PATH=:/opt/jdk1.6.0_38/jre/lib/sparcv9:/opt/jdk1.6.0_38/jre/lib/sparcv9/server)
IID0813009 | [MMSDP] loadtest | E00, E04, E06, ES00 | 2013-08-08 | 2013-08-08 | 1 | Process | Cherdsit Thongsongsuk | TC | Normal | Closed | Pepsi | none | -Should upgrade version and awareness. Roadmap auto script for keep history and revision.
IID0813014 | [ETOPUP] /opt/equinoxAS/bin/EC02: error while loading shared libraries: libjvm.so: cannot open shared object file: No such file or directory | EC02 | 2013-08-14 | 2013-08-14 | 1 | Process | Wanchai Mukdapun | TC | normal | Closed | Fern | none | - /opt/equinoxAS/bin/EC02: error while loading shared libraries: libjvm.so: cannot open shared object file: No such file or directory is occurred while attempting to start EC02 because of this directory has permission denied.
IID0813015 | [OCF] Receive duplicate session. | Unknown | 2013-08-16 |  | 1 | Process | Pawarich Ajanaromwat Bundit Kasemassawachanon | Pheobe | High | On progress | Fern, Pepsi, Tome |  | - There is not enough information to trace.
IID0813019 | [RBTCTF] CER on ES06 | ES06 | 2013-08-21 | 2013-08-26 | 1 | Process | Natkritta Khaminkhao | Niobe | Normal | Closed | Tome |  | -This issue can be fixed by discussion about CER authentication information with diameter server node.
IID0813026 | ES11 build on linux 2.6.18 canot set up on linux 2.6.16 | ES11 | 2013-08-30 |  | 1 | Process |  |  | Norma | On progress | Aof
IID0913005 | [INGW-ETOPUP] ES05 wrong version | ES05 | 2013-09-11 | 2013-09-11 | 1 | Process | Siwanat Ponkhun | TC | High | Closed | Fern |  | -ES05 v.1.5.4 is not support HttpForcePlainText
IID1013017 | [OCF] ec02 internal error | EC02 | 2013-10-15 | 2013-10-15 | 1 |  | Natthaporn Pakdee | QA | Normal | Closed | Pong | none | -this issue is already fixed in EC02 v.3.1.3
IID1113001 | [OCFHK] MsgParserException | EC02 | 2013-11-05 | 2013-11-05 | 1 |  | Pawarich Ajanaromwat | Pheobe | Normal | Closed | Aof, Pong | none
IID1113002 | [OCFHK] IDLE time out | ES03 | 2013-11-08 | 2013-11-08 | 1 |  | Pawarich Ajanaromwat | Pheobe | Normal | Closed | Aof | none | -WARNING¦00:12:31¦7277¦ES03.c¦ber_to_elem¦1498¦Message (0) gone, will discard this message ERROR¦00:12:31¦7277¦ES03.c¦l_clnt_process_msg¦3381¦ber_to_elem return error [] INFO¦00:12:31¦7277¦ES03.c¦l_clnt_close¦3006¦Connection PAUSE
IID1113003 | [OCFHK] SRR timeout | ES06 | 2013-11-08 | 2013-11-08 | 1 |  | Pawarich Ajanaromwat | Pheobe | Normal | Closed | Aof | none

## Equinox Identifier
| Code Name | Version | Build Time
Equinox Relased: | Crowned Eagle | 1.0.0-b2 | 3384
Equinox Relased:
Equinox Relased:
Equinox Relased:
Equinox Relased:
Equinox Process | Version
E00 | 1.0.3.8
E01 | 1.0.1
E03 | 1.0.0.0
E04 | 1.0.2
E06 | 1.0.0.0
E11 | 2.1.3
EC00 | 1.2.4
EC02
ES00 | 1.0.5.10
ES03 | 1.0.0.0
ES04 | 1.0.5.11
ES05 | 1.2.6
ES06 | 1.0.1
ES07 | 1.0.7.13
ES13 | 1.0.2
EQX
DB Utilities